# Metroville Urban Rail Expansion Project - KPI Development

# Technical Feasibility KPIs

## KPI 1:

- KPI Name: Planned vs. Actual Construction Progress

- Definition (What it measures): This measures the percentage of physical construction work (such as track laying and station building) completed compared to what was scheduled for the current time period.

- Measurement Method (How data will be gathered and calculated): Data will be gathered through weekly site inspection reports. The KPI is calculated using the formula:

(Actual % Completed)/(Planned % Completed) * 100

- Rationale (Why this KPI is important): It provides a high-level view of whether the project is on schedule. Identifying delays early allows the project management team to adjust resources before small delays become major setbacks.

## KPI 2:

- KPI Name: Critical Milestone Hit Rate

- Definition (What it measures): This tracks the successful completion of "critical path" milestones—specific events that, if delayed, will push back the entire project end date (e.g., completion of tunneling, safety system installation).

- Measurement Method (How data will be gathered and calculated): This is measured by reviewing the Project Master Schedule at the end of each month. It is calculated as:

(Milestones Completed On Time /Total Milestones Due) * 100

- Rationale (Why this KPI is important): For a complex rail project, not all tasks are equal. Focusing on the critical path ensures that the most vital components of the infrastructure are prioritized to prevent cascading delays.

# Environmental Sustainability KPIs

## KPI 1:

- KPI Name: Construction Waste Diversion Rate

- Definition (What it measures): This measures the percentage of construction debris (concrete, steel, soil) that is recycled or reused rather than being sent to a landfill during the building phase.

- Measurement Method (How data will be gathered and calculated): Contractors will provide waste disposal logs and weight tickets. The calculation is:

(Weight of Recycled Material /Total Weight of Waste Generated) * 100

- Rationale (Why this KPI is important): Large infrastructure projects generate significant waste. Tracking this quantifies the project's immediate environmental footprint and encourages responsible resource management during construction.

## KPI 2:

- KPI Name: Estimated Carbon Footprint Reduction

- Definition (What it measures): This measures the projected annual reduction in CO2 emissions resulting from commuters switching from private cars to the new rail system.

- Measurement Method (How data will be gathered and calculated): This uses traffic modeling data. The calculation estimates:

(Projected Car Miles Avoided * Average Car Emissions) - (Rail Energy Consumption Emissions)

- Rationale (Why this KPI is important): This directly links the rail project to Metroville’s wider green initiatives, demonstrating the long-term environmental return on investment (ROI) to stakeholders and the city government.

# Community Acceptance KPIs

## KPI 1:

- KPI Name: Community Sentiment Index

- Definition (What it measures): A score representing the local community's satisfaction with the project, specifically regarding transparency and construction disruption (noise, traffic detours).

- Measurement Method (How data will be gathered and calculated): Data is gathered via quarterly digital surveys and town hall feedback forms using a 1-5 satisfaction scale. The average score is tracked trend-line over time.

- Rationale (Why this KPI is important): Public opposition can delay projects or increase costs. Monitoring sentiment helps the team identify and address community grievances (like noise levels) before they escalate into protests or bad press.

## KPI 2:

- KPI Name: Service Coverage Expansion

- Definition (What it measures): This measures the number of Metroville households that will gain access to public transit within a 10-minute walk (approx. 800 meters) of the new stations.

- Measurement Method (How data will be gathered and calculated): We will use Geographic Information System (GIS) mapping to overlay the new station locations with population density maps to count the residents in the 800m radius.

- Rationale (Why this KPI is important): This assesses the improvement in accessibility. It proves the project is meeting its social goal of connecting more people to the city network, justifying the investment to the taxpayers.