## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 mi | 67% | 40% | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 mi | 51% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 44% | 30% | 8.82% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| Overall Budget: Overbudget (Tracking to $125M) Electrification: 30 Miles Completed (44%) Track Installed: 48 Miles Total (68%) |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
[5 empty] | Phase 2 | [6 empty] | ←Illustrative
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [8 empty] | Project Financials
[13 empty] | Electrification | 84
[13 empty] | Eastern Section | 73
[13 empty] | Southeastern | 67
[13 empty] | Western Industrial area | 50
[13 empty] | Central Urban | 44
[13 empty] | Spent | 90
[13 empty] | Remaining(Projected) | 35
| Status Update |  | Challenges
| Electrification: Completed 6 new miles; Total is now 30 miles (44%). Southeastern Segment: Installed 4 new miles this week due to equipment upgrades. |  | - Eastern section in risk - Delay due to rocky terrain - 6mi behind schedule ACTION: in progress evaluation of alternative method to expedite progress. - Overspent in the excavation ACTION: Savings on materials have offset this, keeping us within 5% of our overall budget projection for this phase. - Substations construction: Delay in electrical components ACTION: action plan in progress with Buyer
| Community Feedback Highlights |  |  | Risk of schedule delay if night shifts are cancelled to appease noise complaints.
IResidents expressed appreciation for transparency and the opportunity to voice concerns during consultation sessions.
Significant increase in complaints about nighttime noise in the Eastern Section.
Add electrification progress
Add budget tracking